# ResourceConnect - Requirements Review & Analysis

Date: 28 April 2026
Reviewer: Oscar (OpenClaw AI)
Documents Analyzed: - Resource_Tracker_03-Mar-2026.xlsx (Current Excel system) - ResourceConnect-Product-Proposal-FINAL-27April2026.docx (Product specification)

## Executive Summary

Project: Real-Time Resource & Project Management Platform
Target Market: R&D and engineering teams in Life Sciences and similar industries
Organization Size: Small to large organizations (5-50+ resources)
Current State: Excel-based manual system with complex formulas
Proposed State: Web-based real-time collaborative platform

## Current System Analysis (Excel Tracker)

### Data Structure (10 Worksheets)

| Sheet | Purpose | Complexity | Records |
| --- | --- | --- | --- |
| Settings | Global config (dates, hours) | Simple | 4 settings |
| Resources | Team members & capacity | Simple | ~7 resources |
| Projects | Customer projects | Medium | ~15 projects |
| Subtasks | Project work breakdown | Simple | ~13 tasks |
| Assignments | Resource-to-task allocation | High | ~192 assignments |
| Holidays | Company holidays | Simple | ~14 days |
| Annual Leave | PTO tracking | Simple | ~6 entries |
| Daily Load | Per-resource daily hours | Very High | 102 rows × 327 cols |
| Daily FTE Availability | Capacity utilization | Very High | 28 rows × 327 cols |
| Gantt | Visual timeline | High | 153 rows × 334 cols |

### Key Observations

✅ Strengths: 1. Comprehensive data model — All essential entities present 2. Day-level granularity — 327 columns = ~11 months of daily tracking 3. Multi-dimensional views — Load, Availability, Gantt chart 4. Capacity planning — Full-time, half-time, shared resources supported 5. Business context — Client names (Medtronic, Cook), real projects

❌ Pain Points: 1. Formula-heavy — 327 calculated columns per resource per sheet 2. Manual updates — No automation, error-prone data entry 3. Single user — No collaboration, version control issues 4. No real-time visibility — Stakeholders can’t see current state 5. Scalability limits — Excel struggles beyond 20-30 resources 6. No conflict detection — Overallocation only visible after manual inspection 7. Limited reporting — Dashboard requires manual creation

## Core Requirements

### 1. Resource Management

Master Data: - Resource name - Role/title (e.g., “Sr. R&D Engineer”, “Technician IV”) - Capacity (hours/day) — support full-time (7.3h), half-time (3.65h), custom - Notes (e.g., “Shared with Adv.Tech”) - Status (active/inactive)

Derived Needs: - Skills/competencies (not in current Excel, but essential for scaling) - Cost rates (for project costing) - Organizational hierarchy (department, manager) - Location/timezone (for distributed teams)

### 2. Project Management

Project Attributes: - Project name/code - Client/Department - Start date & End date - Status (Planned, Active, On Hold, Complete) - Project manager/owner

Subtask/Work Package Structure: - Hierarchical task breakdown - Subtask codes (e.g., “MDT-LCHT-PO10”) - Estimated hours per task - Dependencies (not visible in Excel, but needed)

### 3. Assignment & Allocation

Core Assignment Data: - Resource → Project → Subtask mapping - Start Date & End Date - Total Hours (for task) - Daily Hours (effort per day) - Notes/comments

Critical Features Missing from Excel: - Conflict detection — Warn when resource allocated >100% - Skill matching — Suggest resources based on requirements - Approval workflow — PM requests resource, manager approves - Historical actuals — Track actual hours vs. planned

### 4. Time Tracking & Availability

Calendar Management: - Company holidays (Irish calendar shown: St. Brigid’s, St. Patrick’s, etc.) - Annual leave/PTO per resource - Working days/hours configuration - Public holiday rules per location

Capacity Calculations: - Daily FTE availability (accounting for holidays, PTO, assignments) - Net available hours per resource per day - Team-level capacity aggregation - Utilization % (allocated / available)

### 5. Visualization & Reporting

Current Excel Views: - Daily Load — Heatmap of hours per resource per day - Daily FTE Availability — Remaining capacity visualization - Gantt Chart — Project timeline view

Web Platform Requirements: - Interactive Gantt — Drag-drop scheduling, zoom levels (day/week/month) - Resource Heatmap — Color-coded overallocation (red), underutilization (yellow), optimal (green) - Dashboard KPIs: - Total projects (Active, Planned) - Team utilization % (current week, month, quarter) - Overallocated resources (count + names) - Upcoming capacity gaps - Real-time updates — Changes reflect immediately for all users

## Functional Requirements

### FR1: Resource CRUD

- Admin can add/edit/delete resources

- Set capacity per resource (default 7.3h/day, customizable)

- Assign roles, departments, cost rates

- Flag resources as active/inactive

### FR2: Project & Task Management

- Create projects with client, dates, status

- Break down projects into subtasks (WBS)

- Assign estimated hours per subtask

- Link subtasks to milestones/deliverables

### FR3: Resource Assignment

- Assign resources to subtasks with date ranges

- Specify daily effort (e.g., 2 hours/day for 10 days)

- Detect conflicts (overallocation warnings)

- Allow partial allocations (50% of day = 3.65 hours)

### FR4: Capacity Planning

- Calculate available hours per resource per day

  - Formula: Capacity - Holidays - PTO - Existing Assignments

- Show utilization % per resource (allocated / available)

- Aggregate team capacity by week/month

- Forecast future availability (3 months, 6 months)

### FR5: Calendar & Time Off

- Configure company holidays per location

- Employees request PTO (approval workflow)

- Block out non-working days (weekends, holidays)

- Support multiple work patterns (5-day, 4-day weeks)

### FR6: Conflict Detection & Alerts

- Red flag: Resource allocated >100% on any day

- Yellow flag: Resource allocated >80% (approaching limit)

- Email/notification when conflicts arise

- Suggest alternative resources with capacity

### FR7: Reporting & Dashboards

- Resource View: See all assignments for a person

- Project View: See all resources on a project

- Timeline View: Gantt chart with dependencies

- Capacity View: Heatmap of team availability

- Utilization Report: % allocated by resource, week, month

- Export: PDF, Excel, CSV for offline review

### FR8: Collaboration & Permissions

- Project Managers: Assign resources to their projects

- Resource Managers: Approve allocations, manage capacity

- Executives: View-only dashboards

- Resources: View their own schedule, request PTO

- Audit Log: Track who changed what when

### FR9: Real-Time Updates

- WebSocket or polling for live updates

- Multiple users can work simultaneously

- Optimistic UI updates (instant feedback)

- Conflict resolution when two users edit the same assignment

### FR10: Mobile Support

- Responsive design (works on tablet/phone)

- Resource view of “My Schedule” on mobile

- PTO request from mobile

- Dashboard snapshot on mobile

## Non-Functional Requirements

### NFR1: Performance

- Load dashboard <2 seconds (up to 50 resources, 100 projects)

- Gantt chart render <3 seconds (12-month view)

- Support 100+ concurrent users

- Real-time updates <500ms latency

### NFR2: Scalability

- Support 5-500 resources without architecture changes

- Handle 1000+ projects over 3-year period

- Archive completed projects (keep 2 years active)

### NFR3: Security

- Role-based access control (RBAC)

- Encrypt sensitive data (cost rates, salaries)

- Audit log (immutable, 7-year retention)

- SSO integration (SAML, OAuth)

### NFR4: Availability

- 99.5% uptime SLA (cloud-hosted)

- Automated backups (daily)

- Disaster recovery plan (4-hour RTO)

### NFR5: Usability

- Onboarding <30 minutes for new users

- Keyboard shortcuts for power users

- Drag-drop scheduling (Gantt chart)

- Undo/redo support for changes

## Technical Architecture Recommendations

### Stack Proposal

Frontend: - React/Next.js (or Vue/Nuxt) for SSR + SPA - TailwindCSS + shadcn/ui components - DHTMLX Gantt or Bryntum Scheduler (commercial) for Gantt charts - Recharts or Chart.js for dashboards - React Query for data fetching + caching

Backend: - Node.js/Express or Python/FastAPI - PostgreSQL (relational data: resources, projects, assignments) - Redis (caching, real-time pub/sub) - WebSockets (Socket.IO or native) for live updates

Deployment: - Docker + Kubernetes (or Fly.io for simpler deployments) - Cloud provider: AWS, GCP, or Azure - CDN for static assets (Cloudflare)

Integrations: - SSO: Auth0, Okta, or Azure AD - Email: SendGrid, Postmark - Calendar: Google Calendar, Outlook sync - Slack/Teams notifications

## Data Model (Simplified ERD)

resources
  - id, name, role, capacity_hours_per_day, cost_rate, status, notes

projects
  - id, name, client, start_date, end_date, status, owner_id

subtasks
  - id, project_id, name, code, estimated_hours, parent_id (hierarchy)

assignments
  - id, resource_id, subtask_id, start_date, end_date, daily_hours, notes

holidays
  - id, date, name, location

pto_requests
  - id, resource_id, start_date, end_date, status (pending/approved/denied), reason

daily_capacity
  - resource_id, date, available_hours (calculated view)

daily_allocation
  - resource_id, date, allocated_hours (sum of assignments)

utilization_snapshot
  - resource_id, week_start, allocated_hours, available_hours, utilization_%

## Migration Strategy (Excel → Web Platform)

### Phase 1: Data Import

- Export Excel sheets to CSV

- Create data ingestion scripts

  - Resources → resources table

  - Projects → projects table

  - Subtasks → subtasks table

  - Assignments → assignments table (flatten Daily Hours into daily records)

  - Holidays → holidays table

  - Annual Leave → pto_requests table

- Validate data integrity (FK constraints, date ranges)

### Phase 2: Feature Parity

- Build CRUD for resources, projects, assignments

- Implement calendar + PTO management

- Recreate Daily Load view (heatmap)

- Recreate Daily FTE Availability view

- Recreate Gantt chart (interactive)

### Phase 3: Enhancements

- Add conflict detection

- Add approval workflows

- Add dashboard/KPIs

- Add real-time updates

- Add mobile-responsive design

### Phase 4: Rollout

- Pilot with 1-2 project managers (2 weeks)

- Train team (1-hour session)

- Run Excel + Web in parallel (1 month)

- Cutover to web-only

- Decommission Excel tracker

## Key Differentiators vs. Existing Tools

Compared to Microsoft Project: - ✅ Simpler UI (less bloated) - ✅ Real-time collaboration - ❌ Less powerful for complex project dependencies

Compared to Resource Guru / Float: - ✅ Custom fit for R&D/Life Sciences workflows - ✅ Subtask-level granularity - ❌ Less polished UI (MVP stage)

Compared to Jira / Monday.com: - ✅ Resource-centric (vs. task-centric) - ✅ Capacity planning focus - ❌ No issue tracking, sprint planning

## Risks & Mitigation

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| User adoption low | High | Medium | Run pilot, gather feedback, iterate |
| Data migration errors | High | Medium | Validate with checksums, parallel run |
| Performance issues at scale | Medium | Low | Load testing, optimize queries, indexing |
| Scope creep | Medium | High | Strict MVP feature freeze, Phase 2 backlog |
| Integration complexity | Low | Medium | Start without integrations, add later |

## Success Metrics

### MVP Success (3 months):

- 80% of project managers using weekly

- 0 overallocation incidents missed

- <2 support tickets per week per team

- Dashboard load time <2 seconds

### Long-Term Success (12 months):

- 100% Excel replacement

- Resource utilization improved by 15%

- Project overruns reduced by 20%

- Time spent on resource planning reduced 50%

## Recommendations

### 1. Start Small (MVP Scope)

In Scope: - Resource CRUD - Project/Subtask CRUD - Assignment CRUD - Calendar + Holidays + PTO - Daily Load heatmap - Basic Gantt chart - Conflict detection (warnings only)

Out of Scope (Phase 2): - Approval workflows - Skill matching - Advanced reporting - Mobile app - Integrations (SSO, Slack, etc.) - Multi-location/multi-currency

### 2. Validate with Users Early

- Show mockups to 3-5 project managers before coding

- Get feedback on Gantt chart UX (critical feature)

- Identify must-haves vs. nice-to-haves

### 3. Leverage Existing Components

- Don’t build Gantt from scratch — use DHTMLX, Bryntum, or similar

- Use Tailwind + shadcn/ui for rapid UI development

- Copy LtecConnect patterns where applicable (similar domain)

### 4. Plan for Multi-Tenancy Later

- Single organization for MVP

- Design data model with tenant_id in mind

- Makes future SaaS expansion possible

## Next Steps

### Immediate (This Week):

- ✅ Review requirements (this document)

- Review ResourceConnect proposal Word doc for alignment

- Create wireframes/mockups (Gantt, Dashboard, Resource view)

- Define MVP scope with Basil

- Estimate development timeline (MVP = 8-12 weeks?)

### Short-Term (Next 2 Weeks):

- Set up project structure (Next.js + PostgreSQL)

- Create database schema + migrations

- Build data import scripts (Excel → PostgreSQL)

- Build first CRUD: Resources

### Medium-Term (Months 1-3):

- Complete MVP features

- Internal testing (LaserTec team)

- Pilot with real data

- Iterate based on feedback

- Production launch

## Questions for Basil

- Target users: Who will use this first? (LaserTec only, or other labs?)

- Hosting preference: Cloud (Fly.io), self-hosted (Mac mini), or both?

- Budget: Any licensing budget for commercial Gantt components (~$1k-5k)?

- Timeline pressure: When do you need MVP live? (3 months? 6 months?)

- Excel coexistence: How long to run both systems in parallel?

- Data sensitivity: Any compliance requirements (GDPR, ISO 13485, FDA)?

- Integration priorities: Any must-have integrations for MVP?

## Conclusion

The Excel Resource Tracker demonstrates a mature understanding of resource management needs for R&D teams in Life Sciences. The data model is comprehensive and well-structured.

Key Value Props of Web Platform: 1. Real-time visibility — Stakeholders see current state without emailing for spreadsheet 2. Conflict prevention — System warns before overallocation, not after 3. Collaboration — Multiple PMs schedule simultaneously without version hell 4. Scalability — Handles 50+ resources, 200+ projects without slowdown 5. Analytics — Built-in utilization reports, capacity forecasts, trend analysis

Recommended Approach: - Build MVP with core features (8-12 weeks) - Pilot with 1-2 teams (LaserTec Engineering + Labs) - Iterate based on feedback - Expand to other organizations (ResourceConnect SaaS)

This has strong potential as both an internal tool (immediate ROI for LaserTec) and a standalone SaaS product (ResourceConnect for similar R&D/engineering organizations in Life Sciences).

Ready to proceed once we align on MVP scope and timeline. 🦌

Document ID: RESOURCECONNECT-REQ-REVIEW-28APR2026
Status: Draft for Review
Next: Mockups + MVP Scoping Session

End of Requirements Review